## Sheet1
| Issue/Enhancement Title | Target Completion Date | Description | User Issue/Functional Issue/Enhancement | Form | Priority
1 | No Categories available | 2018-02-08 | Users with representative access don't see items in the category dropdown when trying to create an entry | User Issue | NP Tracker | 1- High
2 | Add Calendar Year 2018 | 2018-02-08 | Add 2018 to all applicable locations in he tool | Functional Issue | Individual Scorecards, Team Scorecards, Customized Scorecards, NPT, Activity log, Teams | 1- High
3 | Time Off Date | 2018-02-28 | Date selection bugs, you must click the date twice before the bar turns green | Functional Issue | Activity Tracker | 3- Low
4 | NPT Time Display | 2018-02-16 | Add the time spent on an item in the overview display under the NPT Tracker Tab | Enhancement | NP Tracker | 2-Medium
5 | NPT Reporting | 2018-02-28 | Add the ability to sort on column headings and apply filters, as well as export to excel | Enhancement | NP Tracker | 3- Low
6 | Time off Report | 2018-02-28 | Create a report that exports to MS Excel for time tracked in Activity Tracker | Enhancement | Activity Tracker | 3- Low
7 | Formulas on the individual scorecard | 2018-02-16 | I would like to remove the formula from showing on the individual scorecard | Functional Issue | Individual scorecard | 2- Medium
8 | Individual Scorecard Display | 2018-02-09 | Currently Averages include months without data, should only include months with data | Functional Issue | Individual scorecards | 1- High
9 | Filters | 2018-02-16 | Add filters to the headings of all maintenance tabs for easier use | Functional Issue | Representatives, Activity Tracker, NPT Tracker, | 2- Medium
10 | NPT chart | 2/23/2018 ** Tied to output for individual scorecard so may want move up | Show NPT categories and time spent broken down in a donut similar to work types | Functional Issue | Individual scorecards | 2-Medium
11 | Individual Scorecard Export to PDF | 2018-02-11 | Improve the export functionality so a nice looking 2-3 page PDF scorecard can be produced with a click | Functional Issue | Individual scorecards | 1- High
12 | Manager Summary | 2018-02-09 | A manager should be able to pull a summarized group scorecard for all employees | Functional Issue | N/A | 1- High
13 | Dashboard Display | 2018-02-28 | Show a "snap shot" of the most recent user metrics for employees and team summary for managers | Enhancement | Dashboard | 3- Low
14 | Uploaded Data | 2018-02-28 | When trying to determine what data has been loaded into the database it takes a long time to download. I would like to develop a better way to quickly determine what data is in the tool, so someone looking at this tool can see what has been loaded. | Enhancement | Uploaded Data | 3- Low
Note on B2: ALBERT: #1 #2 STATUS: DONE AS OF 02/07 FUNCTIONALITIES ALREADY AVAILABLE IN WEB SERVER (B04WEBD04) - 02/08 TEAMCITY AUTO DEPLOY ISSUES MANUALLY DEPLOYED TO B04WEBD04 ON 02/08 NEED TO VALIDATE FIRST THE WEB SITE IF FUNCTIONING PROPERLY
Note on B4: ALBERT: #3 #4 ALREADY COMPLETED AS OF 02/08 AND FOR DEPLOYMENT TO WEB SERVER (B04WEBD04) TARGET DEPLOYMENT DATE 02/13
Note on B6: ALBERT: #5 #6 #7 #8 #9 STATUS: COMPLETED ON 02/09 TARGET DEPLOYMENT DATE: 02/13 #9 FILTERS - USE FILTER TABLE FUNCTIONALITY OF DATATABLE FRAMEWORK
Note on B11: ALBERT: #10 #11 IN PROGRESS TARGET FINISH DATE: 02/13 TARGET DEPLOYMENT DATE: 02/14 #10 NPT CHART - REUSE BI PRODUCTIVITY PIE CHART COMPONENT FROM THE INDIVIDUAL SCORECARD #11 INDIVIDUAL SCORECARD EXPORT TO PDF - STILL LOOKING FOR A BETTER FRAMEWORK TO REPLACE THE EXISTING FRAMEWORK. DUE TO UNSTABLE COSMETICS RENDERING.
Note on B13: ALBERT: #12 #13 #14 INCLUDED IN THE NEXT SPRNT ITERATION (02/12-02/23) TARGET FINISH DATE: BETWEEN 02/16 - 02/19 TARGET DEPLOYMENT DATE: 02/19 #12 MANAGER SUMMARY (TEAM SUMMARY) #13 DASHBOARD DISPLAY - PART OF TEAM VIEW ENHANCEMENTS WHICH WILL BE PART OF THE NEXT SPRNT ITERATION #14 UPLOADED DATA -